REMOR PROJECT

Implementation Plan

D1.2.

April 2007

Introduction

The Implementation Plan is aimed at providing all Partners of the Remor Project with the necessary guidelines, in order to harmoniously perform the tasks requested and to achieve the objectives and the results expressly indicated in the Grant Agreement.

To this purpose, the Implementation Plan offers a brief description of the Kick Off meeting held in Genoa on the 2nd of April 2007 (par. 1) and describes in details tasks and activities that all Partners should perform to guarantee the harmonious realization of the Project, together with tasks and activities that each single Partner should bring about to obtain the results specifically assigned to the Partner itself (par. 2).

Therefore, in order to develop a network for the exchange of information and mutual knowledge on national legislation of each single Member State involved in Remor Project, all Partners are invited to provide detailed answers to the questionnaire, prepared by the University of Genoa (par. 3).

The questionnaire itself appears to be the quickest and easiest instrument, to gather relevant information and to collect documents on maintenance obligations, which are also useful to help the Riga Graduate School to develop the contents of Remor-website.

Finally, the Implementation Plan provides a specific “timetable” of the tasks and activities that should be performed in compliance with the Project (par. 4 and annex 1).

The University of Genoa recommends that all Partners

- respect the timetable and perform tasks and activities within the time-limits scheduled;

- keep all other Partners - and in particular the University of Genoa - informed on the development of their own tasks and activities;

- cooperate with all other Partners in achieving the objectives of the Project;

- provide their contact details by completing the Remor – contacts form (annex 2) and returning it to the University of Genoa.

1.  Description of the “Kick of Meeting” held at the University of Genoa, 2nd of April 2007

On Monday 2nd April 2007, the Kick of Meeting (hereinafter KOM) of  the Remor Project took place in the meeting room of the Dipartimento G.L.M. Casaregi of the University of Genoa, Faculty of Law.

The KOM was attended by representatives of (i) the University of Genoa (from both sections of Dipartimento G.L.M. Casaregi, section of civil law and section of international and maritime law), (ii) the Romanian National Bar and (iii) the Bar of Genoa.

The meeting was aimed at introducing the Partners attending the event and also at underlining the objectives of the Remor Project and discussing the strategy to achieve them.

The introduction of the Partners attending the meeting was followed by a presentation of the objectives of the project, by the identification of the responsibilities of each Partner and by the indication of activities and tasks completed.

The meeting ended with an explanation of how the budget made available by the Commission was allocated among all Partners (as described in the attached slides, D1.1.).

Activities already completed

Regarding the activities already completed, the University of Genoa, and more precisely the civil law section and the international and maritime law section of the Dipartimento G.L.M. Casaregi, has already realized a collection of materials (legislation, decisions, papers) useful for the research activities.

The University of Genoa has already uploaded the materials collected on the web site of the University of Genoa (http://giurige.aulaweb.unige.it/course/view.php?id=13), in order to make them available for uploading on the Remor web site, as soon as it is ready.

Moreover, the University of Genoa has already scheduled some seminars and workshops.

Finally, the University of Genoa (hereinafter also the Main Partner) asked all other Partners to provide details of their bank accounts in order to transfer the pertinent portion of the budget already allocated  by the Commission.

Activities to be completed

On this basis, the representatives who attended the KOM agreed on the following content of the Implementation plan, establishing the “timetable” of the activities to be performed in compliance with the Remor project (see par. 3 and 4).

In addition to the specific tasks indicated by the Remor Project, the Partners also agreed (i) on the necessity to provide information on specific national legislation and decisions on maintenance obligation and (ii) on the necessity to create a stable network of contacts among all Partners, for the exchange of information and documents.

In order to obtain the result sub (i) , the University of Genoa has set up a questionnaire (see par. 3). The goal of the questionnaire is to enable all Partners envolved in the research to pull information about their own national legislative framework, practical problems and needs that practitioners – such as lawyers and judges - have regularly to face in dealing with maintenance obligation issues.

During the KOM, it was therefore established that each Partner has to provide all materials requested and reply to all questions contained in the questionnaire by the 30 of June 2007.

This questionnaire represents a preliminary activity of fundamental importance in order to achieve the objectives set forth by the Remor Project, with specific reference to the tasks to be performed within the Work package n. 4 (WP4 “Preparation of learning material and research documents” – University of Genoa).

All information and materials required by the questionnaire are of fundamental importance, both for the drafting of documents and papers, analyzing the content of the Regulation proposal and its impact on national systems, and for suggesting suitable changes and/or addittions.

To this purpose, all Partners are also invited to submit the questionnaire to their own “team mates” (i.e. association of lawyers, universities, research centres, etc.) in all member States, in order to bring about the widest and most comprehensive collection of information and materials.

Regarding the necessity of a stable network of contacts among all partners (ii), in addition to the Remor website (which is, of course, the main instrument), during the KOM, it was established that among representatives of all Partners conference calls should take place on a monthly basis, at a jointly established time. To this purpose Skype technology should be used by all Partners.

Once the web site has been established, the University of Genoa proposes to create also a “discussion forum” on specific themes. This instrument is going to be useful to the following: (i) to facilitate the exchange of information on each national system and legislation and (ii) to create stable contacts among the Partners.

2. Activities to be perfomed

In order to achieve the objectives set forth in the Remor Project, each Partner should (i) carry out the tasks that he has been entrusted with (as explained in his own work package) and (ii) should collaborate actively with all other Partners. During the KOM (see point 1), the University of Genoa, as manager and coordinator of the whole project, has scheduled a timetable of activities (see point 4), that each Partner should carry out, being responsible of his own work package.

University of Genoa

Work package 1: project management

Coordinator: Giovanna Savorani

The project management activity is aimed at promoting communication and cooperation among all Partners and at monitoring Project progress. To this purposes, the University of Genoa should (i) facilitate communication between project participants and coordinate the involvement of all Partners; (ii) provide technical, administrative and financial management; (iii) monitor project progress, reporting to the EC and provide a point of communication for the project with the EC; (iv) maintain accurate records of cost and effort; (v)  indicate a range of relevant questions and legal practitioners’ common needs in the subject of the Project; (vi) collect information and documentation; (vii) organize and schedule seminars.

To this purposes, the University of Genoa has already organized the KOM (D1.1, hereby enclosed) and is now delivering the Implementation Plan (D1.2).

By the end of September 2007, the University of Genoa should deliver the Interim Report (D1.3),  in order to inform the Partners on the status quo of the Project. The report should also identify all problems occured, so that they may be overcome.

By the end of January 2008, the University of Genoa should deliver the Final Report (D1.4), in other words a document describing all the activities realized within the Remor Project by the Partners, with specific attention to the “learning activities” done (seminars, lectures, the international conference) and to the main results and experiences gathered throughout the Project. The Final Report should also contain suggestions for the future use of the results of the Project in legal training.

Work package  4: preparation of learning material and research documents

Coordinator: Ilaria Queirolo

This is one of the most important Work Package of the Project; it is aimed at (i) identifying and analyzing a range of relevant questions and legal practitioners’ common needs in the subject of the project; (ii) gathering information and discussion on how to satisfy these needs; (iii) developing deliverables/papers/documents on private international law matters within the European judicial area in the field of maintenance obligations; (iv)  developing a comparative analysis report on the system of circulation of decisions regarding the payment of maintenance obligations; (v)  developing  documents regarding contents of the Proposal of Regulation (COM (2005) 649 def) and its impact on domestic law.

All the following deliverables shall be developed by the end January 2008:

D4.1 Report on relevant questions and legal practitioners’ common needs

D4.2 Comparative analysis report on the system of circulation of decisions regarding the payment of maintenance obligations within the European judicial area

D4.3 Document on critical examination of the contents of the proposal of regulation on jurisdiction, applicable law, recognition and enforcement of decisions and cooperation in matters relating to maintenance obligations

D4.4 Report on the effects of the proposal of regulation COM (2005) 649 def. on member States legislations

D4.5 Paper with advice for suitable changes and completions to proposal of regulation COM (2005) 649

In order to obtain the above mentioned goals, it is of fundamental importance that all Partners cooperate in exchanging information and documents and in fulfilling their own tasks and activities within the time-limits scheduled (see in particular par. 4).

Malta Chamber of Advocates

Work package n. 2: quality assurance

Coordinator: robert g. mangion

This package aims at ensuring  the quality of all projects’ activities and tasks as well as establishing adequate mechanisms to control quality. This quality assurance will be carried out with stakeholders’ feedback.

The Partner in charge of this work package has to arrange the following documents:

- Quality Management Plan (D 2.1), which should serve as a guideline to manage quality control.

The University of Genoa asks the Malta Chamber of Advocates to arrange the Quality Management Plan by the end of May 2007, according to the following guidelines regarding the evaluation of the Project quality: (i) strict respect of the deadlines and time-limits indicated in the Project, (ii) collaboration among all Partners in the exercise of activities and tasks that demand a combined effort; (iii) maintenance of stable contacts with the University of Genoa, as manager and coordinator of the whole Project.

- Interim Quality Management Report (D 2.2), which should explain the quality assurance procedures that the Remor Project will put in place in order to ensure that the project’s outputs comply  with standards and best practices (by the end June  2007).

The University of Genoa, as Main Partner and coordinator of the Remor Project, suggests that the Malta Chamber of Advocates maintains stable contacts with all Partners, through conference calls, using the Skype program.

- Final Quality Management Report (D 2.3), which should include procedures and criteria used to quantify and qualify the Project as a whole and the Work Packages’ separately as well as the legal practitioners’ and stakeholders’ feedback on quality and usefulness. The final document should be produced by the end of January 2008.

The Work package Coordinator should elaborate first the Quality Management Plan and than he should monitor all Patners’ activities and their compliance with established quality guidelines to fulfil the above mentioned Reports.

Referring to the Quality Assurance, all Partners should perform the following tasks: to seek out and consider legal practitioners’ and stakeholders’ feedback; and to comply with the established quality guidelines.

Riga Graduate School of Law

# Work package n.3: project’s webportal and interactive learning

coordinator: Peter Gjoertler

Riga Graduate School of Law should:

- realize Remor project’s web-site (REMOR webportal- D 3.1.) within the end of May 2007;

- provide selection and customization of the interactive platform (REMOR Interactive Learning- D 3.2.) within the end of July 2007;

- continuously update the contents of web-site and platform, uploading files and information about the project, opening discussion groups/fora, providing all materials produced throughout the project in word-pdf-html format, adjourning information on Partners, etc..

The Work package Coordinator should coordinate the appropriate allocation of materials and data collected by the Partners according to Remor Project’s objectives and deadlines. Moreover, the Coordinator should discuss the appropriateness of the selected platform and of the users’ helpdesk. In order to ensure a continuous data’s updating, the Coordinator should monitor the progress of updates and the degree of collaboration (internal/external). Finally, the Coordinator should moderate the discussion forum of this work package (until the end of the Project).

All Partners should collaborate in developing the project’s platform. In particular, they should indicate (i) the different discussion topics of the forum and  (ii) the support staff for the different discussion topics by the end of May 2007. The Partners should also translate and adapt contents (i.e. information and materials) from national languages into English.

With regard to the described activities, the University of Genoa is pleased to inform all Partners that it has already realized an internal web portal, in which relevant documents – which may be useful to develop activities and tasks indicated by the Remor project - have already been uploaded (http://giurige.aulaweb.unige.it/course/view.php?id=13).

Work package n. 5: preparation and realization of seminars and studies

coordinator: Anders Fogelklou

This work package is aimed at:

a) identifying and selecting legal practitioners;

b) identifying the most appropriate learning materials for the lessons;

c) organizing, scheduling, planning seminars (in class and e-seminars) and lectures;

d) experimenting video-streaming lessons;

e) realizing the seminars. In particular, e-seminars and in-class seminars of one week (one in each participating Country), should be held.

In order to achieve the above mentioned results, it would be necessary to carry out some preliminary activities, such as arranging rules for selecting legal practitioners that might be interested in seminars and lectures (by the end of May 2007 – Rules for selection of legal practitioners - D 5.1). With reference to the seminars, the responsible Partner should also

(i) select and prepare learning materials (by the end of May 2007  - Selection and preparation of learning materials for the Remor seminars - D 5.2);

(ii) organize and schedule the courses (by the end of June 2007 – Organization and schedule of the courses - D 5.3);

(iii) write a Report on courses and seminars by the end of January 2008 (Report on courses Deployment - D 5. 4).

The National Association of Romanian Bars

Work package n. 6: evaluation

coordinator: Ligia Danila

This activity aims at evaluating all the activities that should be performed within the Remor Project (from learning activities to research products)

By the end of May 2007 (D6.1), the Coordinator should realize the so-called Evaluation Plan, containing  the criteria for the evaluation of the achieved outcomes.

By the end of January 2008, the Coordinator of the work package should also write the so-called Evaluation Report (D 6.2), pointing out (i) the method and the criteria followed in evaluating the activities carried out in the execution of the project by the Partners and (ii) the results achieved.

It is therefore necessary to establish the External Evaluation Committee, made up of external experts, both in the legal field and in the management of EU projects of this kind. All Partners have to send to the above-mentioned external board all the documents which may be useful for the evaluation activity (i.e. Implementation Plan, Evaluation Plan and Evaluation Report).

The Work package Coordinator has to develop the Evaluation Plan and, thus, he has to evaluate:

- the quality of the products of learning and research activities;

- the participation to the course (identifying also the Country with the highest stakeholders’ contribution and the 10 most active participants to the seminars);

Moreover the Coordinator of this work package has to evaluate the Project overall and to write the Evaluation Report.

In order to achieve the above mentioned objectives, all Partners should assist in the development of the evaluation Plan and in the evaluation processes, by providing all necessary information.

Work package n. 7: valorization/Promotion actions

Coordinator: Alina Cobuz Bagnaru

Within this work package, the Partner will have to take care of the activities of dissemination and exploitation of the deliverables of the Remor Project.

In detail, the Partner will have to realize:

- the brochure ‘Catalogue of Benefits’ (D 7.1) to inform legal practitioners about the benefits on participating in the project and courses (by the end of May 2007);

- the Communication Plan (D 7.2) to deliver guidance and information to Partners on how and when to conduct valorisation/promotion and dissemination activities (by  the end of June 2007);

- Press Releases (D 7.3) to inform on the Projects results at each phase and to foster legal practitioners to the participation at the courses, through articles in national newspapers and magazines (by the end of September 2007)

- (D 7.4) at the end of the Remor Project. The final Internal meeting will be held with the REMOR International Workshop international workshop as a 2-day meeting (23 – 24 November 2007).

- the Valorisation/Promotion Report (D 7.5) to document the conducted valorisation and dissemination activities, including a collection of papers published on international journals (by the end of January 2008).

The work package Coordinator should (i) coordinate and monitor the above-mentioned activities, (ii) draft the “Catalogue of benefits” for participants and (iii) find a strategy to promote the project.

Moreover the Coordinator should identify the most efficient promotion activities (together with local Partners). With reference to workshops/seminars, the Coordinator  should also (i) outline logistics, (ii) draft the invitation of stakeholders/legal practitioners to participate and (iii) form a certificate of participation (by the end of July 2007).

The Coordinator should also assist the University of Genoa in organizing the final international workshop in Italy.

Moreover, the work package Coordinator should establish a “Special Interest Group” to foster collaboration with experts in this and related domains (by the end of June 2007).

All Partners should perform the outlined local promotion activities (like elaboration of press releases, mailings, and targeted banner ads) and should also suggest additional promotion opportunities. Each Partner should (i) organize local seminars and lectures, (ii) provide their assistance in organizing the international workshop, as well as (iii) attend the final international meeting.

3. Standard questionnaire for Remor Partners

As soon as possible and at least by the end of June 2007 the Partners should send to the Main Partner all necessary documents and information required by the questionnaire.

The Partners are also invited to comment on any other matter that they consider relevant to the purposes of the Remor Project and to address the questionnaire itself to other “team mates”, who may also give information and materials on other member States’ systems.

Questionnaire

1. National law on “maintenance obligation” (civil and private international law)

Please provide the Coordinator with all national legislation (both substantive and procedural), soft law measures (i.e. reccomandations, draft of legislative measures) and case-law, which may be relevant to the development of the Remor project’s objectives and connected to the proposal of the Regulation on “maintenance obligation”.

Please note that all documents need to be duly translated in English and submitted on word-pdf-htlm format, so that they can be up-loaded on the web-site.

Regarding private international law, please note that, in addiction to the relevant discipline on competent Authority, applicable law, recognition and execution of decisions, it is necessary to specify whether your Country has ratified international (multilateral or bilateral) treaties on maintenance obligations and/or on any other topic related to maintenance obligations and, if so, please provide the Main Partner with all relevant legislation.

Please specify also if your Country has entered any reservation.

2. What is the “meaning” of maintenance / alimentary /assistance obligation in Your country?

It is necessary to understand what is the concept  that “maintenance” and “maintenance obligation” underlie  according to your domestic law. In particular, we wish to know  if in your Country  there are different legal terms for  maintenance, alimentary and assistance obligations (or, on the contrary, if “maintenance” obligation coveres all kinds and extent of this type of obligation). Please provide the Main Partner with all information useful to define these concepts.

Please specify also whether the concept of maintenance obligation used in your Country is different from the one used by the Court of Justice of the European Communities in its case-law (see in particular C-120/79; C-220/95) and, if so, to what extent.

3. Which is the competent authority to apply to?

Please indicate which courts/administrative bodies within your system have jurisdiction to consider applications on  maintenance obligations. Please specify:

(i) 	whether the competent Authority is a judicial or an administrative body;

(ii)	whether the competent Authority has a specific competence on problems regarding marriage-separation-divorce and or minors;

(iii)	what kind of measures the competent Authority may apply;

(iv)	whether legal aid is required for this sort of proceeding and, if so, on what conditions;

(v)		what procedures and measures exist for the enforcement of the judicial and or administrative orders.

4. Who is entitled to receive maintenance and who is obliged to provide maintenance?

It is therefore important to know the persons to whom the Regulation shall apply. As pointed out in the Green Paper of the Commission on maintenance obligations, the types of relationship that can generate a maintenance obligation between two people vary from one State to another, since sometimes only parents and their children or spouses or ex spouses are concerned, whereas elsewhere the family circle is broader, extending even to living together persons and “civil (or registered) partnership”.

Please indicate:

(i) who is entitled to receive maintenance and who is obliged to provide maintenance under domestic law;

(ii) up to what age and under which condition a child may benefit of a maintenance allowance;

(iii) if your Country has adopted (or is going to adopt) specific legislation on “registered partnership”.

Moreover, the recovery of maintenance is sometimes handled by public agencies, acting on behalf of the creditor or subrogated to the creditor’s rights.

Please indicate whether under your domestic law public bodies/agencies may take an action for the recovery of maintenance obligation. Please provide also any  relevant legislation, case-law, soft law on this specific topic.

5. What are the legal criteria by which manteinance obligations determinations are made?

In particular it is necessary to know

- how maintenance obligations may be fulfilled (i.e. directly, by giving to the beneficiary a determined amount of money or indirectly, as for example by paying costs and/or expenses for services used by the beneficiary);

- whether there is a difference in the legal status of mothers and fathers in providing maintenance obligations towards their child and/or children;

- what determinations are made as regard maintenance obligations towards children in case of joint custody ;

- whether legislation and/or case law provide criteria for the assessment of maintenance obligation (like length of marriage, financial capacity of spouses, etc.), and, in the affirmative, it is important to know them, in order to make a comparative analysis;

- whether in case of breach of obligations arising from the marriage, the right of maintenance might be reduced and/or limited and/or eliminated;

- whether domestic legislation provides automatic adjournment of maintenance obligation taking into account the changes in the costs of living and or other criteria.

Please provide all necessary documents and information at this regard.

6. Is it possible to recover the arrears?

The question of arrears, that is to say the recovery of maintenance awarded by a court but not actually paid, arises in a number of cases. As expressly pointed out in the Green Paper, difficulties can arise in particular if the law of the country where the judgment is to be enforced provides that the judgment awarding maintenance can be enforced, after exequatur, only for future payments, or permits the recovery of arrears only in respect of a limited period.

Regarding this it would be interesting to know (i) whether under domestic law arrears may be awarded and (ii) with specific reference to the enforcement of decisions ordering the payment of arrears, whether limitation rules are regarded as procedural or substantial.

7.  Are the parties (debtor and creditor-beneficiary) free to fix the amount and/or to determine how or who have to pay maintenance?

Please explain whether under domestic law the party entitled to receive maintenance and the party obliged to provide maintenance are free to determine the amount of the payment/obligation and how to pay (i.e. directly, by paying an amount of money to the beneficiary and/or indirectly, by paying for example some specific costs and/or expenses) or whether they have to follow specific criteria and limits indicated by legislation, which has an imperative character.

8. Is it possible to dispose of maintenance obligation (assignability, negotiability, leviablity, seizurability)?

Please give all necessary information on actions and remedies that may be taken in case the maintenance debtor does not pay, in order to force him/her to pay (like seizure orders, salary attachment order, etc.)

Please specify whether third parties may recover their credits on maintenance credits.

9. In which cases, according to domestic law, the beneficiary may lose his right to maintenance?

It is important to know whether under domestic law and/or case law the beneficiary of maintenance obligation may loose his right of maintenance and, in the affirmative, in which cases.

Furthermore, we wish to know whether the ex-spouse may loose his/her right in case he/she starts to live with a new partner.

Please provide all necessary documents and information to this regard.

10. Maintenance/alimentary obligations and private international law matters (applicable law, competent judge, recognition and enforcement of judgements/decisions).

It is necessary to know the relevant legislation on private international law matters.

Please indicate:

- in which cases the law of your Country is applicable (i.e. indicate the conflict of law rules that determine the law applicable to the settlement of an international dispute);

- which law is to be applied when your Country law is not applicable;

- in which cases your judges are competent to take decisions on maintenance obligations;

- what conditions need to be satisfied for the recognition and execution of a foreign decision/judgment;

- whether a foreign decision/judgment establishing right and duty of maintenance between partners living together or “registered partners” may be recognized and enforced or not.

Please provide all necessary documents and information to this regard.

4. Timetable

In order to fulfil all tasks and to realize all activities resulting from the Remor Project, it is necessary that the Partners strictly respect the timetable hereby indicated and established at the end of the KOM by  the University of Genoa.

Starting activities

The Partners have been already provided with an anticipation of the European Commission’s funds, in order to perform some activities, which shall be done before the starting of courses and seminars, such as realization of Quality management plan (D2.1), Organization and schedule of the courses (D5.3), Selection and preparation of learning materials for the Remor seminars (D5.2), realization of Remor Web portal (D3.1) and Interactive learning (D3.2), elaboration of Rules for selection of legal practitioners (D5.1) and of a Brochure informing legal practitioners of the benefits of participating in the projects and courses (D7.1).

In addition to the activities above mentioned, all Partners shall provide all information and materials required by the above questionnaire and eventually can also try to collect further information and documents, by submitting the questionnaire to their own “team mates” in other member States.

The so called “starting activities” are preliminary to the realization of the learning activities (i.e. courses and seminars), therefore shall be duly performed in compliance with the terms of the timetable.

Each single Partner shall therefore fulfil its own tasks within the time limit provided in the schedule hereby enclosed.

Failure to respect the time-limits provided may affect the organization and realization of the “learning activities” and of the entire Project.

It is therefore important that in case of failure each single partner shall

- give prompt notice in writing one week before the expiration of the time-limit to the Coordinator, motivating its failure;

- indicate a new time-limit for the fulfilment of the task not performed, subject to the approval of the Coordinator. In case of urgency, the Coordinator may perform the task or may assign it to another Partner.

Please note that in case of failure by a Partner to fulfil the tasks within the time-limit scheduled, the Coordinator shall stop the transfer of funds provided by the Commission.

All problems that could arise in the realization of the Project and, in particular, in the realization of the so called “starting activities” will be expressly reported in the Interim report (D1.3), that the University of Genoa, as Coordinator, will deliver by the end of September 2007.

Learning activities

All Partners shall organize their own “learning activities”, which may consist in single lectures, workshop, seminars.

By the end of May 2007, all partners shall communicate to the Riga Graduate School a detailed schedule of the seminars, lectures and workshops that have been or will be organized.

Financial reporting

Each Partner shall be able to provide all necessary information and documentation on expenses and costs sustained for the realizations of tasks and activities requested by Remor Project.

Every three months, each Partner shall provide the Coordinator with a detailed report on costs and expenses sustained for Remor Project, together with the inherent documents (i.e. copies of invoices, and receipts; each Partner should keep the originals in its own accounting).

Please note that in case failure by a Partner to provide the Financial Report within the time scheduled, the Coordinator shall stop the transfer of funds provided by the Commission.

Meetings and conference calls

In order to develop a stable network of contacts among the Partners and towards all the future users, the Partners shall cooperate in the realization of the content of the Remor-website and shall provide all information and documents required by Riga Graduate School of Law, as Coordinator  of Work Package n. 3.

In order to develop stable “internal” contacts,  the Partners shall attend the conference calls, which shall take place on a monthly basis.

List of deliverables

Please find hereby indicated the list of deliverables, that the Partners should provide within each single work package.

WP1 Management – University of Genoa - Giovanna Savorani

D.1.1. Kick-off meeting in Italy (PM1) 	April 2,  2007

D.1.2. Implementation plan (PM1)		May 14, 2007

D. 1.3. Interim report (PM6) 			September 2007

D. 1.4. Final report (PM12)			January 2008

WP2  Quality assurance – Malta Chamber of Advocates – Robert G. Mangion

D2.1 Quality management plan		May 2007

D2.2 Quality management report		June 2007

D2.3 Quality management final report	January 2008

WP3 Project’s Web portal and interactive learning – Riga Graduate School – Peter Gjoertler

D3.1 Remor Web portal			May 2007

D3.2 Remor Interactive Learning		July 2007

WP4 Preparation of learning material and research documents – University of Genoa – Ilaria Queirolo

D4.1 Report on relevant questions and legal practitioners’ common needs	January 2008

D4.2 Comparative analysis report on the system of circulation of decisions regarding the payment of maintenance obligations within the European judicial area	                        January 2008

D4.3 Document on critical examination of the contents of the proposal of regulation on jurisdiction, applicable law, recognition and enforcement of decisions and cooperation in matters relating to maintenance obligations	                                                                      January 2008

D4.4 Report on the effects of the proposal of regulation COM (2005) 649 def. on member States legislations	                                                                                              January 2008

D4.5 Paper with advice for suitable changes and completions to proposal of regulation COM (2005) 649	                                                                                                           January 2008

WP5 Preparation and realization of seminars and studies – Riga Graduate School pf Law – Anders Fogelklou

D5.1 Rules for selection of legal practitioners				            	 May 2007

D5.2 Selection and preparation of learning materials for the Remor seminars	May 2007

D5.3 Organization and schedule of the courses					June 2007

D5.4 Report on the courses deployment						January 2008

WP6  Evaluation – The National Association of Romanian Bars - Ligia Danila

D6.1 Evaluation Plan and External Evaluation Committee				May 2007

D6.2 Evaluation Report								January 2008

WP7 Valorisation actions – The National Association of the Romanian Bars – Alina Cobuz Bagnaru

D7.1 Brochure “Catalogue of Benefits” printed and digitalized, to inform legal practitioners about the benefits on participating in the Project and about courses available; distribution: mailings, seminars and conferences.  								                   May 2007

D7.2 Communication Plan: to deliver guidelines and information to the Partners on how and when to conduct valorisation and dissemination activities					       June 2007

D7.3 Press releases: to inform on the project results at each phase and to foster legal practitioners to participate in the courses through articles in newspapers and/or scientific reviews. Distribution: newspapers, magazines, conference papers, internet. 				              September 2007

D7.4 Remor International workshop: held in Italy with the participation of all Partners (the purpose is the presentation of the results and initiation of a public debate on the subject of the Project). The final internal meeting will be held together with an international workshop as a 2-day meeting to obtain a proper valorisation and diffusion of the results of the activities after the end of the Project and to discuss conclusions and results.						              November 2007

D7.5 Valorisation Report: to document the valorisation of the Project, in particular the diffusion of the activities, including  the papers published or still in the process of being published.  January 2008

List of annexes:

- Scheme of Remor timetable

- Remor Contacts form