## Foglio1
Remor Project - Timetable
Remor Partners |  | # | Tasks to be performed | Mese
|  |  |  | 2007-03-01 | 2007-04-01 | may-07 | jun-07 | 2007-07-01 | aug-07 | sep-07 | oct-07 | 2007-11-01 | dec-07 | jan-08 | 2008-02-01
1 | University of Genoa WP1 e WP4 | 1 | Kick off meeting KOM D1.1
|  | 2 | Implementation plan D1.2
|  | 3 | Interim report D1.3
|  | 4 | Final report D1.4
|  | 5 | Report D4.1
|  | 6 | Report D4.2
|  | 7 | Document D4.3
|  | 8 | Report D4.4
|  | 9 | Paper D4.5
|  | 10 | Questionnaire
|  | 11 | Financial report
2 | Riga GLS WP3 e WP5 | 12 | Remor Webportal D3.1
|  | 13 | Remor Interactive Learning D3.2
|  | 14 | Rules for selection D5.1
|  | 15 | Learning materials D5.2
|  | 16 | Organization courses D5.3
|  | 17 | Report on course D5.4
|  | 18 | Questionnaire
|  | 19 | Financial report
3 | UNB Romania WP6 e WP7 | 20 | Evaluation Plan D6.1
|  | 21 | Evaluaton Report D6.2
|  | 22 | Brochure D7.1
|  | 23 | Communication Plan D7.2
|  | 24 | Press releases D7.3
|  | 25 | Remor international workshop D7.4
|  | 26 | Valorisation report D7.5
|  | 27 | Questionnaire
|  | 27 | Financial report
4 | Malta Chambers of Advocates WP2 | 28 | Quality management plan D2.1
|  | 29 | Quality management report D2.2
|  | 30 | Quality management final report D2.3
|  | 31 | Questionnaire
|  | 32 | Financial report
* | Conference call among all partners on a monthly basis
Each single task shall be performed by the end of the month indicated.