Annex n. 4

Evaluation Plan

Remor Project aims at analyzing the Commission’s proposal of Regulation on maintenance obligation and its impact on Member State’s legal order.

To this purpose, the Partners will (i) develop learning activities on this topic; (ii) deliver research products (i.e. papers, articles, books).

In order to evaluate the quality of the performance of the Remor Project’s tasks, the National Association of Romanian Bar (hereinafter NARB) will adopt the following criteria:

1. learning activities

The NARB will take into account all the initiatives promoted by member States (i.e. workshop, seminars, lectures, meetings).

In order to evaluate the initiatives promoted, specific attention will be paid to:

(i) the initiatives themselves, which will be considered under two different criteria:

- number of the initiatives realized;

- involvement of other Partners and/or of other institutions (both academic and professional).

(ii) the participants to each single initiative, having specific regard to two different criteria:

- the number of the participants to each single initiatives;

- the qualification of each single participant (student, lawyer, judge, other persons who have professional interest in the subject considered).

In order to be able to evaluate these aspects, each Partner at the beginning of each single initiative promoted, shall ask the participant to fill a schedule containing some information (like name, surname, nationality, qualification, the reason/interest for participating to the meeting, the mean by which each participant have received notice of the event).

At the end of each single event, the responsible Partner shall deliver to the NARB a short report,

- describing the event itself and indicating the Partners and/or other institutions involved;

- rationalizing all data collected from the participants through the schedules and indicating the number of all participants, pointing out how many students, lawyers, judges and “other persons” attended the event.

All reports collected shall be delivered by NARB to an External Committee, composed by (three) experts on EU law and/or management on EU research programs: 1. Prof. Ruth Faruggia; 2. Pres. Adriano Sansa; Prof. Roberto Baratta.

The External Committee. on the basis of the data collected, will evaluate relevance of the event, by considering

a) the degree of involvement of other Partners and/or institutions (insufficient, sufficient, good, very good);

b) the degree of participation to the event (insufficient, sufficient, good, very good).

The External Committee will therefore deliver its own opinion both on each single event and on all learning activities realized within the project.

2. Research products

The NARB will collect and list all deliverables and/or products of the research activities  (i.e. papers, articles, books) and prepare a brief scheme, pointing out:

- the authors and their qualification,

- the main recipients of the products;

- the relevance of the products for the performance of the tasks of the Remor Project.

Both research products and NARB’s schemes will be delivered to the External Committee, which will give its own opinion on them, having specific regard to:

- the quality of the product itself (insufficient, sufficient, good, very good);

- the relevance of the product for the performance of the Remor Project’s tasks.

The External Committee will therefore deliver its own opinion both on each single research product and on all products realized by the Partners within the Remor Project.